## Instructions
INSTRUCTIONS
Before beginning to use these spreadsheets, please do the following:
1) | At the top of this screen, go to Tools, then Options, then Calculations.
In the area of the window called Workbook options (near the bottom of the window),
Make certain that "Precision as displayed" is checked. This will eliminate any problems due to roundoff.
2) | Enter the project number, description, county, scope of work, project length,
the name of your firm and all applicable rates on the GRAND TOTAL FEE sheet.
(This information will be copied to the other sheets automatically.)
3) | Please remember to submit man-day and fee proposals for any and all subconsultants. Failure to do so will
result in delays.
4) | You must use the out-of-pocket expense sheet(s) included in this set of spreadsheets.
5) | Do not submit a proposal for preliminary plans unless you are specifically requested to do so
or the scope of work for your project contains preliminary plans.
6) | You may have to revise these spreadsheets to match your specific scope of work.

## GRAND TOTAL FEE
Project No.
County
Description
Scope of Work
Project Length | 0 | Miles
Consultant
GRAND TOTAL OF FEE PROPOSAL
Corridor Study |  |  | 0
Field Surveys |  |  | 0
Preliminary Roadway Plans |  |  | 0
Preliminary Bridge Plans |  |  | 0
Right-of-Way Map, Tract Sketches and Deeds |  |  | 0
Roadway Plans |  |  | 0
Bridge Plans |  |  | #VALUE!
|  | GRAND TOTAL FEE | #VALUE!
Combined overhead rate (%) >>>>>>>>>>>>>>> | 0
Facilities Capital Cost of Money (if used) >>>>>> | 0
LABOR RATES
Classification | Daily Rate
Project Manager | 0
Engineer | 0
Environmental | 0
Engineering Technician/CADD | 0
Environmental Technician | 0
Clerical | 0
PLS | 0
Survey Crew | 0
**Certification of Out-of-Pocket Expenses:
If Out-of-Pocket Expenses are included in this proposal, we hereby certify that these costs are not
included in the Combined Overhead Rate and are typically invoiced to all clients as a direct job cost.
_______________________ _________
| Signed |  | Date
_______________________
| Position/Title | Position Title
Mileage reimbursement | 0.575 | per mile | as of 01-01-20
Note on A1: Enter the appropriate information in the areas shaded in green. It will be copied to all other sheets automatically.
Note on A20: INSERT RATES BELOW (they will be copied to other sheets automatically)
Note on A37: If your proposal contains out-of-pocket expenses, please read the statement below, then sign and date below.
Note on B21: Enter your firm's combined overhead rate here.
Note on B23: If your firm has a Facilities Capital Cost of Money, enter it here.
Note on B27: Enter the daily rates here (as appropriate). If you have multiple personnel in one classification, you must use weighted-average rates.

## Corridor (Man-days)
Project No.
County
Description
Scope of Work
| Project Length | 0 | Miles
Consultant
CORRIDOR STUDY
|  | Engineer | Engineer. Tech. | Environment | Environ. Tech. | Clerical
Task A: Preliminary Corridor Investigation
A-1 Obtain & Study State Supplied Maps |  | 0 | 0 | 0 | 0 | 0
A-2 Prepare Corridor Base Maps, Identify Features & Env. Sensitive Areas |  | 0 | 0 | 0 | 0 | 0
A-3 Consult With Various Agencies, Ascertain Their Requirements |  | 0 | 0 | 0 | 0 | 0
A-4 Develop General Design Criteria for Each Reasonable Alternate |  | 0 | 0 | 0 | 0 | 0
A-5 Perform a Capacity Analysis for Each Design Alternate |  | 0 | 0 | 0 | 0 | 0
A-6 Develop Study Report and Present to State and FHWA |  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
Task A Totals |  | 0 | 0 | 0 | 0 | 0
Task B: Alternative Upgrading Studies
B-1 Develop and Study Preliminary Alternate Designs to Determine Feasibility |  | 0 | 0 | 0 | 0 | 0
B-2 Tabulate ROW Requirements for All Alternates/Develop Cost Estimates |  | 0 | 0 | 0 | 0 | 0
B-3 Conduct Environmental Studies/Develop Alternative Matrix |  | 0 | 0 | 0 | 0 | 0
B-4 Prepare Information for and Attend Public Inv. Meeting / Analyze Comments |  | 0 | 0 | 0 | 0 | 0
B-5 Review Feasible Alternates & Prepare Environmental Assessment |  | 0 | 0 | 0 | 0 | 0
B-6 Prepare Information for and Attend Corridor Hearing / Analyze Comments |  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
Task B Totals |  | 0 | 0 | 0 | 0 | 0
Task C: Engineering Analysis on Selected Alternative
C-1 Refine Selected Alternate and Prepare Layout Map and Profile/Study Report |  | 0 | 0 | 0 | 0 | 0
C-2 Prepare FONSI on Preferred Alternate/Submit for Review & Approval |  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
Task C Totals |  | 0 | 0 | 0 | 0 | 0
TOTALS |  | 0 | 0 | 0 | 0 | 0

## Corridor (Fee)
Project No.
County
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Fee Proposal (Corridor Study)
PERSONNEL COST
Man-days x Daily Rate
Project Manager (10% of Eng. & Env.) | 0 | 0 | 0
Engineer | 0 | 0 | 0
Engineering Technician/CADD | 0 | 0 | 0
Environmental | 0 | 0 | 0
Environmental Technician | 0 | 0 | 0
Clerical | 0 | 0 | 0
| Total Direct Labor |  | 0
Combined Overhead (%) | 0 |  | 0
Out-of-Pocket Expenses** |  |  | 0
|  | Sub-Total | 0
Operating Margin (15%) |  |  | 0
|  | Sub-Total | 0
SUB-CONSULTANTS (attach man-day & fee FROM each sub-consultant; show total fee for each here)
0
0
0
0
0
0
Subconsultant Administration Expense (5%) |  |  | 0
|  | Sub-Total | 0
Facilities Capital Cost of Money (% of Direct Labor) | 0 |  | 0
|  | TOTAL FEE | 0
**See Grand Total Fee sheet

## Corridor (Expense)
Project No. | #REF!
County | #REF!
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Out-of-pocket Expenses (Corridor Study)
TRAVEL COST
Mileage Cost |  | Trips | Miles/Trip | $/Mile | Total
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  |  | Total Mileage Cost |  | 0
Subsistence Cost |  | Days | # People | $/Day | Total
Travel allowance (6 hour trips) |  | 0 | 0 | 11.25 | 0
Travel allowance (12 hour trips - meal provided by others) |  | 0 | 0 | 20 | 0
Travel allowance (12 hour trips) |  | 0 | 0 | 30 | 0
Travel allowance (overnight)*** |  | 0 | 0 | 75 | 0
|  | 0 | 0 | 0 | 0
|  |  | Total Subsistence Cost |  | 0
|  |  | Total Travel Cost |  | 0
PRINTING / REPRODUCTION COST
Type of printing/reproduction | # of Sets | Sheets/Set | Total Sheets | Cost/Sheet | Total
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  | Total Printing/Reproduction Cost |  |  | 0
Communication Cost (telephone, fax, etc.) |  |  |  |  | Total
0
Postage Cost (overnight, stamps, etc.) |  |  |  |  | Total
0
Other (provide description on next line) |  |  |  |  | Total
0
|  | Total Out-of-pocket Expenses |  |  | 0
Comments:
***You must have ALDOT approval for ANY overnight trips of less than 100 miles.
Note on A11: Insert description of trip here
Note on A12: Insert description of trip here
Note on A13: Insert description of trip here
Note on A14: Insert description of trip here
Note on A28: Enter type of printing/reproduction here
Note on A29: Enter type of printing/reproduction here
Note on A30: Enter type of printing/reproduction here
Note on A31: Enter type of printing/reproduction here
Note on A32: Enter type of printing/reproduction here
Note on A33: Enter type of printing/reproduction here
Note on F37: Enter estimated cost of communication here
Note on F40: Enter estimated cost of postage here
Note on F43: Enter other cost here

## Survey(Man-days)
Project No.
County
Description
Scope of Work
|  | Project Length | 0 | Miles
Consultant
FIELD SURVEY
|  |  | PLS | Crew | Tech/CADD | Clerical
Based on a | 0 | Man Crew
Task A: Mobilization and Basic Control Survey
A-1 Mobilize/Demobilize |  |  | 0 | 0 | 0 | 0
A-2 Contact Property Owners |  |  | 0 | 0 | 0 | 0
A-3 Perform Basic Control Survey |  |  | 0 | 0 | 0 | 0
A-4 Conduct On-site Inspection |  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
Task A Totals |  |  | 0 | 0 | 0 | 0
Task B: Project Alignment and Profile
B-1 Run Closure of Basic Control Survey/Prepare Closure Diagram |  |  | 0 | 0 | 0 | 0
B-2 Establish Centerline/Obtain Ground Profile |  |  | 0 | 0 | 0 | 0
B-3 Obtain Topographic Data |  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
Task B Totals |  |  | 0 | 0 | 0 | 0
Task C: Supplemental Control Surveys and Data Gathering
C-1 Traverse Cross-Roads and Railroads |  |  | 0 | 0 | 0 | 0
C-2 Stream Topography & Cross Sections/Complete HYD-100 & 101 Forms |  |  | 0 | 0 | 0 | 0
C-3 Define Drainage Areas/Prepare Schematic Drainage Map |  |  | 0 | 0 | 0 | 0
C-4 Obtain Cross-Sections at 20 Meter Intervals and Ground Break Points |  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
Task C Totals |  |  | 0 | 0 | 0 | 0
Task D: Utility Surveys, Drainage Sections and Compilation of Data
D-1 Identify/Locate Utilities |  |  | 0 | 0 | 0 | 0
D-2 Obtain Hydrological Location Survey |  |  | 0 | 0 | 0 | 0
D-3 Tie All Available Section Corners & All Available Front Corners
of Affected Properties to Project Centerline |  |  | 0 | 0 | 0 | 0
D-4 Obtain Copies of Latest Deeds |  |  | 0 | 0 | 0 | 0
D-5 Set & Reference PIs, PCs, POTs, POCs, & other critical points |  |  | 0 | 0 | 0 | 0
D-6 Reduce Survey Field Notes |  |  | 0 | 0 | 0 | 0
D-7 Submit Work for Review/Sealed Mylar Plot of Accepted Field Map |  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
Task D Totals |  |  | 0 | 0 | 0 | 0
TOTALS |  |  | 0 | 0 | 0 | 0

## Survey(Fee)
Project No.
County
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Fee Proposal (Field Survey)
PERSONNEL COST
Man-days x Daily Rate
Project Manager (10% of PLS) | 0 | 0 | 0
PLS | 0 | 0 | 0
Survey Crew (see man-day sheet) | 0 | 0 | 0
Engineering Technician/CADD | 0 | 0 | 0
Clerical | 0 | 0 | 0
| Total Direct Labor |  | 0
Combined Overhead (%) | 0 |  | 0
Out-of-Pocket Expenses** |  |  | 0
|  | Sub-Total | 0
Operating Margin (15%) |  |  | 0
|  | Sub-Total | 0
SUB-CONSULTANTS (attach man-day & fee FROM each sub-consultant; show total fee for each here)
0
0
0
Subconsultant Administration Expense (5%) |  |  | 0
|  | Sub-Total | 0
Facilities Capital Cost of Money (% of Direct Labor) | 0 |  | 0
|  | TOTAL FEE | 0
**See Grand Total Fee sheet

## Survey (Expense)
Project No. | #REF!
County | #REF!
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Out-of-pocket Expenses (Field Survey)
TRAVEL COST
Mileage Cost |  | Trips | Miles/Trip | $/Mile | Total
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  |  | Total Mileage Cost |  | 0
Subsistence Cost |  | Days | # People | $/Day | Total
Travel allowance (6 hour trips) |  | 0 | 0 | 11.25 | 0
Travel allowance (12 hour trips - meal provided by others) |  | 0 | 0 | 20 | 0
Travel allowance (12 hour trips) |  | 0 | 0 | 30 | 0
Travel allowance (overnight)*** |  | 0 | 0 | 75 | 0
|  | 0 | 0 | 0 | 0
|  |  | Total Subsistence Cost |  | 0
|  |  | Total Travel Cost |  | 0
PRINTING / REPRODUCTION COST
Type of printing/reproduction | # of Sets | Sheets/Set | Total Sheets | Cost/Sheet | Total
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  | Total Printing/Reproduction Cost |  |  | 0
Communication Cost (telephone, fax, etc.) |  |  |  |  | Total
0
Postage Cost (overnight, stamps, etc.) |  |  |  |  | Total
0
Other (provide description on next line) |  |  |  |  | Total
0
|  | Total Out-of-pocket Expenses |  |  | 0
Comments:
***You must have ALDOT approval for ANY overnight trips of less than 100 miles.
Note on A11: Insert description of trip here
Note on A12: Insert description of trip here
Note on A13: Insert description of trip here
Note on A14: Insert description of trip here
Note on A28: Enter type of printing/reproduction here
Note on A29: Enter type of printing/reproduction here
Note on A30: Enter type of printing/reproduction here
Note on A31: Enter type of printing/reproduction here
Note on A32: Enter type of printing/reproduction here
Note on A33: Enter type of printing/reproduction here
Note on F37: Enter estimated cost of communication here
Note on F40: Enter estimated cost of postage here
Note on F43: Enter estimated cost of postage here

## Prelim Rdwy & Bridge (Man-days)
Project No.
County
Description
Scope of Work
| Project Length | 0 | Miles
Consultant
PRELIMINARY ROADWAY & BRIDGE PLANS
|  |  |  | Engineer | Technician/CADD
Roadway
Phase I
1. Assemble and review all existing studies, plans and reports |  |  |  | 0 | 0
2. Develop design criteria for all roadways and submit to State |  |  |  | 0 | 0
3. Perform conceptual traffic analysis for the design year |  |  |  | 0 | 0
4. Establish conceptual design alternates |  |  |  | 0 | 0
5. Develop typical sections |  |  |  | 0 | 0
6. Review/confirm location of grade separations |  |  |  | 0 | 0
7. Identify potential hazardous waste sites |  |  |  | 0 | 0
8. Coordinate with railroad, utility and other companies as needed |  |  |  | 0 | 0
9. Meet with State/FHWA to determine alternates to be carried forward |  |  |  | 0 | 0
Phase I Totals |  |  |  | 0 | 0
Phase II
1. Prepare preliminary design plans of selected alternates |  |  |  | 0 | 0
2. Make adjustments in main roadway profile to optimize its location |  |  |  | 0 | 0
3. Place existing and proposed major drainage facilities on layout |  |  |  | 0 | 0
4. Submit request for ROW and utility cost estimates |  |  |  | 0 | 0
5. Perform detailed traffic analysis/Prepare and submit traffic analysis report |  |  |  | 0 | 0
6. Prepare cost estimate for each alternate |  |  |  | 0 | 0
7. Present preliminary design plans to State/FHWA for review |  |  |  | 0 | 0
8. Attend and present the preliminary plans at Public Involvement Meeting |  |  |  | 0 | 0
9. Analyze and resolve comments from Public Involvement Meeting |  |  |  | 0 | 0
10. Meet with State/FHWA to determine design to be carried forward |  |  |  | 0 | 0
Phase II Totals |  |  |  | 0 | 0
Phase III
1. Provide State with 3 sets of plan rolls for the entire project |  |  |  | 0 | 0
2. Perform access study by developing alternates to provide access |  |  |  | 0 | 0
3. Compare cost of providing access vs. cost of damages for loss of access |  |  |  | 0 | 0
4. Provide recommendations for providing access to each tract in a report |  |  |  | 0 | 0
Phase III Totals |  |  |  | 0 | 0
Phase IV
1. Make necessary revisions/complete preliminary design plans |  |  |  | 0 | 0
2. Submit locations of haz. mat. sites & UST's to the State |  |  |  | 0 | 0
3. Make appropriate revisions to cost estimate |  |  |  | 0 | 0
4. Present preliminary plans to State/FHWA for review |  |  |  | 0 | 0
5. Attend Design Hearing |  |  |  | 0 | 0
6. Analyze and resolve comments from Design Hearing |  |  |  | 0 | 0
7. Provide narrative of sequence of construction concept |  |  |  | 0 | 0
8. Provide conceptual signing plans |  |  |  | 0 | 0
9. Present preliminary design plans and recommendations to State/FHWA |  |  |  | 0 | 0
10. Furnish deliverables to State at completion of project |  |  |  | 0 | 0
|  |  |  | 0 | 0
Phase IV Totals |  |  |  | 0 | 0
PRELIMINARY ROADWAY TOTALS |  |  |  | 0 | 0
Bridge
1. Prepare preliminary span layouts (TS&L) plans for all required bridges |  |  |  | 0 | 0
2. Furnish preliminary cost estimates of each alternative bridge |  |  |  | 0 | 0
|  |  |  | 0 | 0
PRELIMINARY BRIDGE TOTALS |  |  |  | 0 | 0
PRELIMINARY PLANS TOTALS |  |  |  | 0 | 0
Note on A9: Please do not use this form (Preliminary Plans) unless you have been instructed to do so and/or Preliminary Plans are listed in your scope of work.

## Preliminary Roadway Plans(Fee)
Project No.
County
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Fee Proposal (Preliminary Roadway Plans)
PERSONNEL COST
Man-days x Daily Rate
Project Manager (10% of Eng.) | 0 | 0 | 0
Engineer | 0 | 0 | 0
Engineering Technician/CADD | 0 | 0 | 0
Clerical | 0 | 0 | 0
| Total Direct Labor |  | 0
Combined Overhead (%) | 0 |  | 0
|  | Sub-Total | 0
Out-of-Pocket Expenses** |  |  | 0
|  | Sub-Total | 0
Operating Margin (15%) |  |  | 0
|  | Sub-Total | 0
SUB-CONSULTANTS (attach man-day & fee FROM each sub-consultant; show total fee for each here)
0
0
0
Subconsultant Administration Expense (5%) |  |  | 0
|  | Sub-Total | 0
Facilities Capital Cost of Money (% of Direct Labor) | 0 |  | 0
|  | TOTAL FEE | 0
**See Grand Total Fee sheet
Note on B8: Please do not use this form (Preliminary Plans) unless you have been instructed to do so and/or Preliminary Plans are listed in your scope of work.
Note on B15: Insert clerical man-days here

## Prelim. Roadway (Expense)
Project No. | #REF!
County | #REF!
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Out-of-pocket Expenses (Preliminary Roadway Plans)
TRAVEL COST
Mileage Cost |  | Trips | Miles/Trip | $/Mile | Total
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  |  | Total Mileage Cost |  | 0
Subsistence Cost |  | Days | # People | $/Day | Total
Travel allowance (6 hour trips) |  | 0 | 0 | 11.25 | 0
Travel allowance (12 hour trips - meal provided by others) |  | 0 | 0 | 20 | 0
Travel allowance (12 hour trips) |  | 0 | 0 | 30 | 0
Travel allowance (overnight)*** |  | 0 | 0 | 75 | 0
|  | 0 | 0 | 0 | 0
|  |  | Total Subsistence Cost |  | 0
|  |  | Total Travel Cost |  | 0
PRINTING / REPRODUCTION COST
Type of printing/reproduction | # of Sets | Sheets/Set | Total Sheets | Cost/Sheet | Total
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  | Total Printing/Reproduction Cost |  |  | 0
Communication Cost (telephone, fax, etc.) |  |  |  |  | Total
0
Postage Cost (overnight, stamps, etc.) |  |  |  |  | Total
0
Other (provide description on next line) |  |  |  |  | Total
0
|  | Total Out-of-pocket Expenses |  |  | 0
Comments:
***You must have ALDOT approval for ANY overnight trips of less than 100 miles.
Note on A11: Insert description of trip here
Note on A12: Insert description of trip here
Note on A13: Insert description of trip here
Note on A14: Insert description of trip here
Note on A28: Enter type of printing/reproduction here
Note on A29: Enter type of printing/reproduction here
Note on A30: Enter type of printing/reproduction here
Note on A31: Enter type of printing/reproduction here
Note on A32: Enter type of printing/reproduction here
Note on A33: Enter type of printing/reproduction here
Note on F37: Enter estimated cost of communication here
Note on F40: Enter estimated cost of postage here
Note on F43: Enter estimated cost of postage here

## Preliminary Bridge Plans(Fee)
Project No.
County
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Fee Proposal (Preliminary Bridge Plans)
PERSONNEL COST
Man-days x Daily Rate
Project Manager (10% of Eng.) | 0 | 0 | 0
Engineer | 0 | 0 | 0
Engineering Technician/CADD | 0 | 0 | 0
Clerical | 0 | 0 | 0
| Total Direct Labor |  | 0
Combined Overhead (%) | 0 |  | 0
|  | Sub-Total | 0
Out-of-Pocket Expenses** |  |  | 0
|  | Sub-Total | 0
Operating Margin (15%) |  |  | 0
|  | Sub-Total | 0
SUB-CONSULTANTS (attach man-day & fee FROM each sub-consultant; show total fee for each here)
0
0
0
Subconsultant Administration Expense (5%) |  |  | 0
|  | Sub-Total | 0
Facilities Capital Cost of Money (% of Direct Labor) | 0 |  | 0
|  | TOTAL FEE | 0
**See Grand Total Fee sheet
Note on B8: Please do not use this form (Preliminary Plans) unless you have been instructed to do so and/or Preliminary Plans are listed in your scope of work.
Note on B15: Insert clerical man-days here

## Prelim. Bridge (Expense)
Project No. | #REF!
County | #REF!
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Out-of-pocket Expenses (Preliminary Bridge Plans)
TRAVEL COST
Mileage Cost |  | Trips | Miles/Trip | $/Mile | Total
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  |  | Total Mileage Cost |  | 0
Subsistence Cost |  | Days | # People | $/Day | Total
Travel allowance (6 hour trips) |  | 0 | 0 | 11.25 | 0
Travel allowance (12 hour trips - meal provided by others) |  | 0 | 0 | 20 | 0
Travel allowance (12 hour trips) |  | 0 | 0 | 30 | 0
Travel allowance (overnight)*** |  | 0 | 0 | 75 | 0
|  | 0 | 0 | 0 | 0
|  |  | Total Subsistence Cost |  | 0
|  |  | Total Travel Cost |  | 0
PRINTING / REPRODUCTION COST
Type of printing/reproduction | # of Sets | Sheets/Set | Total Sheets | Cost/Sheet | Total
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  | Total Printing/Reproduction Cost |  |  | 0
Communication Cost (telephone, fax, etc.) |  |  |  |  | Total
0
Postage Cost (overnight, stamps, etc.) |  |  |  |  | Total
0
Other (provide description on next line) |  |  |  |  | Total
0
|  | Total Out-of-pocket Expenses |  |  | 0
Comments:
***You must have ALDOT approval for ANY overnight trips of less than 100 miles.
Note on A11: Insert description of trip here
Note on A12: Insert description of trip here
Note on A13: Insert description of trip here
Note on A14: Insert description of trip here
Note on A28: Enter type of printing/reproduction here
Note on A29: Enter type of printing/reproduction here
Note on A30: Enter type of printing/reproduction here
Note on A31: Enter type of printing/reproduction here
Note on A32: Enter type of printing/reproduction here
Note on A33: Enter type of printing/reproduction here
Note on F37: Enter estimated cost of communication here
Note on F40: Enter estimated cost of postage here
Note on F43: Enter estimated cost of postage here

## ROW Estimate
Project No.
County
Description
Scope of Work
| Project Length | 0 | Miles
Consultant
Supporting Documentation for ROW Fee Proposal
Date of Research | Parcel Tax ID # | # of Tracts
| Total Tracts: | 0

## ROW(Man-days)
Project No.
County
Description
Scope of Work
| Project Length | 0 | Miles
Consultant
ROW Map, Tract Sketches and Deeds
|  |  |  | Engineer | Tech/CADD | Clerical
Estimated number of tracts= |  | 0
Task A: Right-of-Way Map |  |  |  | 0 | 0 | 0
Task B: Tract Sketches |  |  |  | 0 | 0 | 0
Task C: Deeds |  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
TOTALS |  |  |  | 0 | 0 | 0
Note: A "Tract" is all property of a single owner acquired by ALDOT. This includes all parcels, drainage easements,
construction easements, etc.

## ROW(Fee)
Project No.
County
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Fee Proposal (ROW Map, Tract Sketches & Deeds)
PERSONNEL COST
Man-days x Daily Rate
Project Manager (10% of Eng.) | 0 | 0 | 0
Engineer | 0 | 0 | 0
Engineering Technician/CADD | 0 | 0 | 0
Clerical | 0 | 0 | 0
| Total Direct Labor |  | 0
Combined Overhead (%) | 0 |  | 0
Out-of-Pocket Expenses** |  |  | 0
|  | Sub-Total | 0
Operating Margin (15%) |  |  | 0
|  | Sub-Total | 0
SUB-CONSULTANTS (attach man-day & fee FROM each sub-consultant; show total fee for each here)
0
0
0
Subconsultant Administration Expense (5%) |  |  | 0
|  | Sub-Total | 0
Facilities Capital Cost of Money (% of Direct Labor) | 0 |  | 0
|  | TOTAL FEE | 0
**See Grand Total Fee sheet

## ROW (Expense)
Project No. | #REF!
County | #REF!
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Out-of-pocket Expenses (ROW Map, Tract Sketches & Deeds)
TRAVEL COST
Mileage Cost |  | Trips | Miles/Trip | $/Mile | Total
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  |  | Total Mileage Cost |  | 0
Subsistence Cost |  | Days | # People | $/Day | Total
Travel allowance (6 hour trips) |  | 0 | 0 | 11.25 | 0
Travel allowance (12 hour trips - meal provided by others) |  | 0 | 0 | 20 | 0
Travel allowance (12 hour trips) |  | 0 | 0 | 30 | 0
Travel allowance (overnight)*** |  | 0 | 0 | 75 | 0
|  | 0 | 0 | 0 | 0
|  |  | Total Subsistence Cost |  | 0
|  |  | Total Travel Cost |  | 0
PRINTING / REPRODUCTION COST
Type of printing/reproduction | # of Sets | Sheets/Set | Total Sheets | Cost/Sheet | Total
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  | Total Printing/Reproduction Cost |  |  | 0
Communication Cost (telephone, fax, etc.) |  |  |  |  | Total
0
Postage Cost (overnight, stamps, etc.) |  |  |  |  | Total
0
Other (provide description on next line) |  |  |  |  | Total
0
|  | Total Out-of-pocket Expenses |  |  | 0
Comments:
***You must have ALDOT approval for ANY overnight trips of less than 100 miles.
Note on A11: Insert description of trip here
Note on A12: Insert description of trip here
Note on A13: Insert description of trip here
Note on A14: Insert description of trip here
Note on A28: Enter type of printing/reproduction here
Note on A29: Enter type of printing/reproduction here
Note on A30: Enter type of printing/reproduction here
Note on A31: Enter type of printing/reproduction here
Note on A32: Enter type of printing/reproduction here
Note on A33: Enter type of printing/reproduction here
Note on F37: Enter estimated cost of communication here
Note on F40: Enter estimated cost of postage here
Note on F43: Enter estimated cost of postage here

## Roadway Plans (Man-days)
| Project Number |  |  |  | CPMS #
County
Description
Scope of work
| Length | 0 | miles
Consultant
ROADWAY PLANS |  |  |  | NO OF | ESTIMATED MAN-DAYS
|  |  |  | SHEETS | ENGINEER |  | TECHNICIAN
| SHEET TITLE |  |  |  | SHEET | TOTAL | SHEET | TOTAL
TITLE SHEET |  |  |  | 0 | 0 | 0 | 0 | 0
INDEX SHEET |  |  |  | 0 | 0 | 0 | 0 | 0
GEOMETRIC LAYOUT/SURVEY CONTROL |  |  |  | 0 | 0 | 0 | 0 | 0
PROJECT NOTE SHEET (Project) |  |  |  | 0 | 0 | 0 | 0 | 0
PROJECT NOTE SHEET (TCP) |  |  |  | 0 | 0 | 0 | 0 | 0
PROJECT NOTE SHEET (Signage) |  |  |  | 0 | 0 | 0 | 0 | 0
PROJECT NOTE SHEET (Signals) |  |  |  | 0 | 0 | 0 | 0 | 0
PROJECT NOTE SHEET (ITS) |  |  |  | 0 | 0 | 0 | 0 | 0
PROJECT NOTE SHEET (Lighting) |  |  |  | 0 | 0 | 0 | 0 | 0
PROJECT NOTE SHEET (Traffic Loops) |  |  |  | 0 | 0 | 0 | 0 | 0
PLANS LEGEND & ABBREVIATIONS |  |  |  | 0 | 0 | 0 | 0 | 0
TYPICAL SECTIONS
Main Roadway |  |  |  | 0 | 0 | 0 | 0 | 0
Cross Roads |  |  |  | 0 | 0 | 0 | 0 | 0
Detour & Misc. |  |  |  | 0 | 0 | 0 | 0 | 0
Ramps |  |  |  | 0 | 0 | 0 | 0 | 0
Ditches |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
SUMMARY SHEET
Main Summary |  |  |  | 0 | 0 | 0 | 0 | 0
SUMMARY BOX SHEETS
Roadway Drainage (non-culvert) |  |  |  | 0 | 0 | 0 | 0 | 0
Culvert Extension, New Culvert |  |  |  | 0 | 0 | 0 | 0 | 0
Bridge Culvert Extension, New Bridge Culvert |  |  |  | 0 | 0 | 0 | 0 | 0
Guardrail/End Anchors |  |  |  | 0 | 0 | 0 | 0 | 0
Slope Paving (Under Bridges) |  |  |  | 0 | 0 | 0 | 0 | 0
Side Drain Pipe |  |  |  | 0 | 0 | 0 | 0 | 0
Signing |  |  |  | 0 | 0 | 0 | 0 | 0
Base & Pavement |  |  |  | 0 | 0 | 0 | 0 | 0
Bridge |  |  |  | 0 | 0 | 0 | 0 | 0
Striping & Pavement Markings |  |  |  | 0 | 0 | 0 | 0 | 0
Curb & Gutter |  |  |  | 0 | 0 | 0 | 0 | 0
Bridge End Slabs |  |  |  | 0 | 0 | 0 | 0 | 0
Roadway Lighting |  |  |  | 0 | 0 | 0 | 0 | 0
Signals |  |  |  | 0 | 0 | 0 | 0 | 0
ITS |  |  |  | 0 | 0 | 0 | 0 | 0
Sidewalk |  |  |  | 0 | 0 | 0 | 0 | 0
Slope Paving (Ditches)/Ditch Summary |  |  |  | 0 | 0 | 0 | 0 | 0
Concrete Safety Barrier |  |  |  | 0 | 0 | 0 | 0 | 0
Retaining Wall |  |  |  | 0 | 0 | 0 | 0 | 0
Misc. Boxes |  |  |  | 0 | 0 | 0 | 0 | 0
Erosion Control |  |  |  | 0 | 0 | 0 | 0 | 0
Removal Items |  |  |  | 0 | 0 | 0 | 0 | 0
Utility Relocation |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
PLAN & PROFILE
Main Roadway |  |  |  | 0 | 0 | 0 | 0 | 0
Crossroads |  |  |  | 0 | 0 | 0 | 0 | 0
Detours |  |  |  | 0 | 0 | 0 | 0 | 0
Retaining Walls |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
PAVING LAYOUT (includes striping)
Main Roadway |  |  |  | 0 | 0 | 0 | 0 | 0
Crossroads |  |  |  | 0 | 0 | 0 | 0 | 0
Intersections |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
INTERCHANGES
Geometrics |  |  |  | 0 | 0 | 0 | 0 | 0
Ramps Profiles |  |  |  | 0 | 0 | 0 | 0 | 0
Site Grading |  |  |  | 0 | 0 | 0 | 0 | 0
Cross Sections |  |  |  | 0 | 0 | 0 | 0 | 0
Signing |  |  |  | 0 | 0 | 0 | 0 | 0
Ramp Gore Details |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
TRAFFIC CONTROL
Sequence of Construction |  |  |  | 0 | 0 | 0 | 0 | 0
Summary & Items |  |  |  | 0 | 0 | 0 | 0 | 0
Typical Section Sketches |  |  |  | 0 | 0 | 0 | 0 | 0
Layout Sheets (signs, devices, shifts, etc.) |  |  |  | 0 | 0 | 0 | 0 | 0
Special Drawings |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
SIGNING
Sign Layout |  |  |  | 0 | 0 | 0 | 0 | 0
Sign X-Section |  |  |  | 0 | 0 | 0 | 0 | 0
Sign Panel Details |  |  |  | 0 | 0 | 0 | 0 | 0
Soils Data Sheets (provided by ALDOT) |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
SIGNALIZATION
Signal Layout and Traffic Analysis (1 per site) |  |  |  | 0 | 0 | 0 | 0 | 0
Traffic Counts (1 per site) |  |  |  | 0 | 0 | 0 | 0 | 0
Signal Warrant Analysis (1 per site) |  |  |  | 0 | 0 | 0 | 0 | 0
Soils Data Sheets (provided by ALDOT) |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
ITS
Systems Engineering |  |  |  | 0 | 0 | 0 | 0 | 0
Special Study |  |  |  | 0 | 0 | 0 | 0 | 0
Legend |  |  |  | 0 | 0 | 0 | 0 | 0
Special Details |  |  |  | 0 | 0 | 0 | 0 | 0
ITS Layouts |  |  |  | 0 | 0 | 0 | 0 | 0
Optical Fiber Splice Charts |  |  |  | 0 | 0 | 0 | 0 | 0
Fiber - Cable Routing Diagram |  |  |  | 0 | 0 | 0 | 0 | 0
Specifications |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
LIGHTING
Plan Layout |  |  |  | 0 | 0 | 0 | 0 | 0
Demo Plans |  |  |  | 0 | 0 | 0 | 0 | 0
Special Details |  |  |  | 0 | 0 | 0 | 0 | 0
Soils & Passive Pressure (provided by ALDOT) |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
UTILITY SHEETS
Utility Locations (plan/profile) |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
DRAINAGE SECTIONS
Pipe & Culvert X-Sect./Hydraulic Computations |  |  |  | 0 | 0 | 0 | 0 | 0
Hydraulic Data Sheet |  |  |  | 0 | 0 | 0 | 0 | 0
Details |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
SOIL SHEETS
Soil Boring Logs |  |  |  | 0 | 0 | 0 | 0 | 0
Soil Profile |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
EROSION CONTROL
Legend & Sequence |  |  |  | 0 | 0 | 0 | 0 | 0
Phased Sheets (Phase I) |  |  |  | 0 | 0 | 0 | 0 | 0
Phased Sheets (Phase II) |  |  |  | 0 | 0 | 0 | 0 | 0
Phased Sheets (Phase III) |  |  |  | 0 | 0 | 0 | 0 | 0
CBMPP & NOI |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
ROADWAY CROSS SECTIONS
Main Roadway |  |  |  | 0 | 0 | 0 | 0 | 0
Crossroads |  |  |  | 0 | 0 | 0 | 0 | 0
Earthwork Balancing |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
REVIEW COMMENTS
30% Review | [5 empty] | 0 |  | 0
Plan-in-Hand Inspection | [5 empty] | 0 |  | 0
PS&E Inspection | [5 empty] | 0 |  | 0
Cost Estimates | [5 empty] | 0 |  | 0
Design Hearing | [5 empty] | 0 |  | 0
SUB-TOTAL |  |  |  | 0 |  | 0 |  | 0
10% Supervision | [5 empty] | 0
TOTALS |  |  |  | 0 |  | 0 |  | 0

## Roadway Plans (Fee)
Project No. | #REF!
County | #REF!
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Fee Proposal (Roadway Plans)
PERSONNEL COST
Man-days x Daily Rate
Project Manager (10% of Eng.) | 0 | 0 | 0
Engineer | 0 | 0 | 0
Engineering Technician/CADD | 0 | 0 | 0
Clerical | 0 | 0 | 0
| Total Direct Labor |  | 0
Combined Overhead (%) | 0 |  | 0
Out-of-Pocket Expenses** |  |  | 0
|  | Sub-Total | 0
Operating Margin (15%) |  |  | 0
|  | Sub-Total | 0
SUB-CONSULTANTS (attach man-day & fee FROM each sub-consultant; show total fee for each here)
0
0
0
Subconsultant Administration Expense (5%) |  |  | 0
|  | Sub-Total | 0
Facilities Capital Cost of Money (% of Direct Labor) | 0 |  | 0
|  | TOTAL FEE | 0
**See Grand Total Fee sheet
Note on B15: Insert clerical man-days here

## Roadway (Expense)
Project No. | #REF!
County | #REF!
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Out-of-pocket Expenses (Roadway Plans)
TRAVEL COST
Mileage Cost |  | Trips | Miles/Trip | $/Mile | Total
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  |  | Total Mileage Cost |  | 0
Subsistence Cost |  | Days | # People | $/Day | Total
Travel allowance (6 hour trips) |  | 0 | 0 | 11.25 | 0
Travel allowance (12 hour trips - meal provided by others) |  | 0 | 0 | 20 | 0
Travel allowance (12 hour trips) |  | 0 | 0 | 30 | 0
Travel allowance (overnight)*** |  | 0 | 0 | 75 | 0
|  | 0 | 0 | 0 | 0
|  |  | Total Subsistence Cost |  | 0
|  |  | Total Travel Cost |  | 0
PRINTING / REPRODUCTION COST
Type of printing/reproduction | # of Sets | Sheets/Set | Total Sheets | Cost/Sheet | Total
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  | Total Printing/Reproduction Cost |  |  | 0
Communication Cost (telephone, fax, etc.) |  |  |  |  | Total
0
Postage Cost (overnight, stamps, etc.) |  |  |  |  | Total
0
Other (provide description on next line) |  |  |  |  | Total
0
|  | Total Out-of-pocket Expenses |  |  | 0
Comments:
***You must have ALDOT approval for ANY overnight trips of less than 100 miles.
Note on A11: Insert description of trip here
Note on A12: Insert description of trip here
Note on A13: Insert description of trip here
Note on A14: Insert description of trip here
Note on A28: Enter type of printing/reproduction here
Note on A29: Enter type of printing/reproduction here
Note on A30: Enter type of printing/reproduction here
Note on A31: Enter type of printing/reproduction here
Note on A32: Enter type of printing/reproduction here
Note on A33: Enter type of printing/reproduction here
Note on F37: Enter estimated cost of communication here
Note on F40: Enter estimated cost of postage here
Note on F43: Enter estimated cost of postage here

## Bridge Plans (Man-days)
FEE COMPUTATIONS FOR PREPARING BRIDGE DESIGN & PLANS
Consultant:
Submittal Date: |  | PROJECT NO:
DESCRIPTION:
COUNTY:
SHEET TITLE |  |  | NO. OF | CONSULTANT ESTIMATED MANDAYS
|  |  | SHEETS | ENGR. | TOTAL | TECH. | TOTAL
|  |  |  | days/sheet | DAYS | days/sheet | DAYS
Preliminary Bridge Layout |  |  | 0 | 0 | 0 | 0 | 0
Index, Notes, Quantities, & Required |  |  | 0 | 0 | 0 | 0 | 0
Bridge General Plan & Elevation |  |  | 0 | 0 | 0 | 0 | 0
|  | SUBTOTAL | 0 |  | 0 |  | 0
BRIDGE SUPERSTRUCTURE DESIGN & DETAIL
Span Details |  |  | 0 | 0 | 0 | 0 | 0
Girder Details |  |  | 0 | 0 | 0 | 0 | 0
Bearings, Diaphragms, Miscellaneous Details |  |  | 0 | 0 | 0 | 0 | 0
| SUBTOTAL per SPAN |  | 0 |  | 0 |  | 0
Number of individual spans/girders requiring design and detail |  |  |  | 0
|  | SUBTOTAL | 0 |  | 0 |  | 0
Will bridge be in vertical curve or superelevation/transition? |  |  |  | y
Enter "y" for yes, enter "n" for no
Incremental (1/10 point) Elevations (when required) |  |  | 0 | 0 | 0 | 0 | 0
BRIDGE SUBSTRUCTURE DESIGN & DETAIL
Abutment Details |  |  | 0 | 0 | 0 | 0 | 0
Number of individual abutments requiring design and detail
|  | SUBTOTAL | 0 |  | 0 |  | 0
Bent Details |  |  | 0 | 0 | 0 | 0 | 0
Number of individual bents requiring design and detail
|  | SUBTOTAL | 0 |  | 0 |  | 0
Complexity Effort - (entered as mandays) additional effort required due
to complexity of design such as skew, horiz. and vertical curve
SHOP DRAWING REVIEW
Prestressed Girders |  |  |  |  | 0
| TOTALS - Total # Shts |  | 0 | Engr. Days | 0 | Tech. Days | 0

## Bridge Plans (Fee)
FEE COMPUTATIONS FOR BRIDGE PLANS
Consultant: |  |  |  | PROJECT NO:
DESCRIPTION:
COUNTY:
EMPLOYEE WAGES:
Project Manager (10% of Engineer)
| >>>>>>>>> |  | 0 | Days |  | 0 | per Day | =
| Engineer |  | 0 | Days | x | 0 | per Day | =
| Technician |  | 0 | Days | x | 0 | per Day | =
TOTAL DIRECT LABOR
Combined Overhead (%) |  | >>>>> | 0 | % | x |  |  | = | #VALUE!
0
[6 empty] | SUBTOTAL COSTS |  | = | #VALUE!
[6 empty] | Out-of-pocket expense** |  | = | 0
[6 empty] | PROFIT (15%) |  | = | #VALUE!
[6 empty] | TOTAL BRIDGE FEE |  | = | #VALUE!
**See Grand Total Fee sheet

## Bridge (Expense)
Project No. | #REF!
County | #REF!
Description
Scope of Work
Project Length | 0 | Miles
Consultant
Out-of-pocket Expenses (Bridge Plans)
TRAVEL COST
Mileage Cost |  | Trips | Miles/Trip | $/Mile | Total
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  | 0 | 0 | 0.575 | 0
|  |  | Total Mileage Cost |  | 0
Subsistence Cost |  | Days | # People | $/Day | Total
Travel allowance (6 hour trips) |  | 0 | 0 | 11.25 | 0
Travel allowance (12 hour trips - meal provided by others) |  | 0 | 0 | 20 | 0
Travel allowance (12 hour trips) |  | 0 | 0 | 30 | 0
Travel allowance (overnight)*** |  | 0 | 0 | 75 | 0
|  | 0 | 0 | 0 | 0
|  |  | Total Subsistence Cost |  | 0
|  |  | Total Travel Cost |  | 0
PRINTING / REPRODUCTION COST
Type of printing/reproduction | # of Sets | Sheets/Set | Total Sheets | Cost/Sheet | Total
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  | Total Printing/Reproduction Cost |  |  | 0
Communication Cost (telephone, fax, etc.) |  |  |  |  | Total
0
Postage Cost (overnight, stamps, etc.) |  |  |  |  | Total
0
Other (provide description on next line) |  |  |  |  | Total
0
|  | Total Out-of-pocket Expenses |  |  | 0
Comments:
***You must have ALDOT approval for ANY overnight trips of less than 100 miles.
Note on A11: Insert description of trip here
Note on A12: Insert description of trip here
Note on A13: Insert description of trip here
Note on A14: Insert description of trip here
Note on A28: Enter type of printing/reproduction here
Note on A29: Enter type of printing/reproduction here
Note on A30: Enter type of printing/reproduction here
Note on A31: Enter type of printing/reproduction here
Note on A32: Enter type of printing/reproduction here
Note on A33: Enter type of printing/reproduction here
Note on F37: Enter estimated cost of communication here
Note on F40: Enter estimated cost of postage here
Note on F43: Enter estimated cost of postage here