A G R E E M E N T

**BETWEEN**

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**AND**

**STATE OF ALABAMA**

**ACTING BY AND THROUGH**

**THE ALABAMA DEPARTMENT OF TRANSPORTATION**

**CONSTRUCTION ENGINEERING AND INSPECTION SERVICES**

**STATEWIDE**

# A G R E E M E N T

# CONSTRUCTION ENGINEERING AND INSPECTION SERVICES

 This AGREEMENT is made and entered into by and between the State of Alabama, acting by and through its Alabama Department of Transportation, (ALDOT), hereinafter referred to as the STATE, and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, which is qualified to do business in the State of Alabama, and has its principal Alabama office at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, Party of the Second Part, hereinafter referred to as the CONSULTANT.

 WHEREAS, the CONSULTANT has agreed and by these present does agree with the STATE for the consideration hereinafter mentioned to provide on-call construction engineering and inspection, materials sampling and testing and contract administration on a statewide basis for the STATE.

 NOW, THEREFORE, for and in consideration of the mutual covenants hereinafter stipulated, it is hereby agreed between the parties as follows:

 The CONSULTANT shall meet the requirements for conformance with the Standards adopted by AASHTO and approved by the Secretary of Transportation in cooperation with the STATE and shall ascertain the written practices of the STATE prior to beginning any work on this project. All work required under this AGREEMENT will be performed in accordance with these standard practices and any special requirements hereinafter set forth. All work performed by the CONSULTANT under this AGREEMENT shall be subject to the Review, Approval and Acceptance of the STATE and Federal Highway Administration, where applicable, before CONSULTANT will be paid for said work.

 “As a part of obligations of the CONSULTANT to the STATE under this AGREEMENT, the CONSULTANT does hereby certify that CONSULTANT has no financial or other interest in the outcome of project proposed under this AGREEMENT”.

 The CONSULTANT shall provide on-call construction engineering and inspection, materials sampling and testing and contract administration on a statewide basis for the STATE.

This will be a specific rate of pay AGREEMENT for a two-year period. The CONSULTANT shall provide services, personnel and equipment as required by the STATE.

**ARTICLE I - SCOPE OF WORK**

The CONSULTANT will perform construction engineering and inspection, materials sampling and testing and contract administration services on-call on a statewide basis for the STATE.

This will be a specific rate of pay AGREEMENT for a two-year period. The CONSULTANT will provide services, personnel and equipment as required by the STATE. The work to be performed by the CONSULTANT will be as follows:

**SECTION 1 - CONSTRUCTION ENGINEERING AND INSPECTION SERVICES**

1.0 PURPOSE:

This statement of work describes and defines services which are required for construction engineering, inspection, materials sampling and testing and contract administration for construction projects selected by the STATE.

2.0 SCOPE:

The CONSULTANT shall be responsible for all construction engineering and administrative functions as defined in this Scope of Work and referenced manuals and procedures. The CONSULTANT shall utilize effective control procedures to assure the construction of said project is performed in reasonable conformity with plans, specifications and contract provisions for assigned project.

The CONSULTANT shall provide professional, technical and administrative personnel, meeting requirements of the STATE in appropriate numbers at proper times to ensure that responsibilities assigned under this AGREEMENT are effectively fulfilled. All services shall be performed in accordance with established standard procedures and practices of the STATE. Prior to furnishing any services, the CONSULTANT shall be familiar with ALDOT procedures, standard and informal, and practices, standard and informal, for construction, engineering and contract administration used by the STATE. The STATE shall endeavor to provide the CONSULTANT at least ten (10) calendar days advance notice of the execution date for each construction contract to allow sufficient time for the CONSULTANT to schedule its activities. In the event of emergency needs, for a short-term basis (sickness, vacation, etc.), the STATE shall provide the CONSULTANT two days advance notice in order for the CONSULTANT to furnish required personnel. The CONSULTANT shall maintain close coordination with the STATE and the Contractor to minimize rescheduling of the CONSULTANT’S activities due to construction delays or changes in scheduling of the Contractor's activities.

1. DEFINITIONS:
2. Transportation Director: The chief executive officer of ALDOT.
3. Deputy Director, Operations: The individual appointed by the Transportation Director to administer operations phases of ALDOT

C. Chief Engineer: The individual appointed by the Transportation Director to administer technical phases of ALDOT.

D. Construction Bureau: The Bureau of ALDOT charged with administering ALDOT’S construction program.

E. State Construction Engineer: Administrative head of the Bureau of Construction of ALDOT.

F. Project Manager, CONSULTANT: Qualified individual who has been assigned as the on-site person in charge of a construction contract.

Project Manager, STATE: Qualified individual assigned by the STATE to manage Construction Engineering and Inspection contract formulated by this AGREEMENT and will be in responsible charge and direct control of project.

G. FHWA: The Federal Highway Administration of the United States Department of Transportation.

H. Construction Contract: Construction work let under separate contract(s) by ALDOT to contracting firm(s).

I. Contractor: Contracting firm or its designated representatives awarded contract(s) to do construction work.

J. Construction Contract Suspension: Cessation of construction activity on a construction contract.

K. Region Engineer: Administrative head of ALDOT’S Region.

L. District Administrator: Administrative head of one of ALDOT’S Districts.

M. State Bridge Engineer: Administrative head of ALDOT’S Bridge Bureau.

N. State Design Engineer: Administrative head of ALDOT’S Design Bureau.

O. Consultant: Consultant firm(s) retained by ALDOT to perform all construction engineering and administrative functions as defined in this AGREEMENT.

P. State Materials and Tests Engineer: Administrative head of ALDOT’S Materials and Tests Bureau.

Q. Area Materials Engineer: Employee designated by ALDOT to administer policies on materials sampling and testing in ALDOT’S Region/Area.

R. Consultant Design Engineer (when applicable): Consultant design engineer retained by ALDOT to design aforementioned project(s).

1. Area Construction Engineer: Employee designated by ALDOT to administer policies and procedures of construction projects covered by this AGREEMENT in ALDOT’S Region/Area.
2. Region/Area Consultant CE & I Engineer/Manager (when applicable): Employee of ALDOT designated by Region/Area Construction Engineer to be in charge of project(s) covered by this AGREEMENT.
3. Area Local Transportation Engineer (when applicable): Employee of ALDOT that administers policies and procedures of city and county construction projects let by ALDOT.
4. County Engineer: Administrative head of the County Engineering Department.
5. City Engineer: Administrative head of the Mayor’s Office/City Engineering Department.

4.0 ITEMS TO BE FURNISHED BY THE STATE TO CONSULTANT:

A. The minimum Contract documents for each project shall be distributed to the CONSULTANT, via the Region/Area Engineer, by ALDOT’S Office Engineer subsequent to award of construction contract for each project as follows:

 5 sets Construction Plans - Half scale

3 sets Construction Plans - Full size (1 set to be used in preparation of as built plans)

 2 sets Standard Drawings

 1 copy of Executed Contract

1. An adequate supply of all standard forms to be used in fulfilling technical services under this AGREEMENT, disposable type molds for casting concrete test cylinders, sample cartons, sample bags and other expendable-type testing supplies. The CONSULTANT may use computerized forms approved by ALDOT. Construction and Materials Management Software including CAMMS, SiteManager, Stormwater Tracking System and Concrete Management System will be used for contract administration on designated projects.
2. When determined by the Region Engineer, the STATE will furnish and maintain a Project Office at a location. The office will include shall meet all local, state and federal building codes and requirements and shall contain the following:
3. A minimum 600 square feet heated and cooled office space.
4. Floor space shall be divided into one restroom, one central work room and three private offices.
5. Heating, air conditioning and lighting.
6. Water cooler service (not bottled water).
7. Hot and cold water service.
8. If the office is a trailer, tie downs capable of withstanding winds up to hurricane force and trailer underpinning.
9. Garbage and trash disposal service.
10. Grass and weed control.
11. Parking spaces for a minimum of five (5) vehicles; graded for drainage and suitably surfaced with an all-weather access road.
12. The STATE shall provide janitorial service.
13. Restroom connections to an existing sanitary sewer, a chemical holding tank, or approved septic tank.
14. The minimum furniture shall be supplied as follows:

Per office – 1 desk, 3 chairs

Per work room – 1 plan table, 1 work table (drafting), 2 stools, 3 chairs, 1 water cooler dispenser, 1-4 drawer file cabinet, 10 feet of book shelving, 1 plan storage rack and appropriate fire extinguishers.

1. The STATE shall provide computers, typewriters, calculators, etc. for STATE personnel and one telephone for each office and work room. The CONSULTANT shall be required to provide computers, tablet computers, smart phones, calculators, etc. for their personnel if needed to perform duties. All computers, tablet computers and smart phones provided by the CONSULTANT shall comply with the requirements listed in Article 1, Section 1, Paragraph 5.B.14 of this AGREEMENT.
2. The STATE shall provide a facsimile machine and a copier for use by the STATE and consultant personnel. The CONSULTANT shall be allowed to furnish personal equipment for his own use at no cost to the STATE.
3. The STATE shall provide testing equipment, photographic equipment, tapes, rulers, field books and other miscellaneous items necessary for satisfactory performance of work.
4. The CONSULTANT shall provide all surveying equipment and it must be the latest technical equipment such as electronic total stations, data collection, hand-held computers, automatic levels, hand-held two-way radios, electronic pipe and cable locators and complete safety equipment.
5. Routine items for operation of the office such as stamps, postal costs, utility service, etc., shall be supplied by the STATE.

5.0 ITEMS FURNISHED BY THE CONSULTANT:

A. Document Compliance

The requirements outlined within printed documents listed below are a condition of this contract. The CONSULTANT shall obtain, without cost to STATE, at least one copy of each document. One copy of each document shall be available at project office at all times. Compliance with these guides, manuals, procedures, and advisories shall be a requirement of this AGREEMENT.

1. Applicable ALDOT Standard Specifications for Highway Construction with one copy for each of the CONSULTANT'S personnel.
2. ALDOT’S Construction Manual. This manual describes in detail many of the procedures and practices of ALDOT relating to construction engineering and inspection. (Said manual is available on ALDOT’S website)

 3. All active Construction Information Memorandums issued, prior to or after execution of this AGREEMENT, by ALDOT’S State Construction Engineer. These procedures convey certain practices and procedures of ALDOT relating to construction supervision and administration of contracts. A copy of each Memorandum issued on or subsequent to execution of this AGREEMENT shall be furnished to the CONSULTANT in a timely manner by ALDOT’S Region Construction Engineer. (Said manual is available on ALDOT’S website)

 4. ALDOT’S Testing Manual as issued by ALDOT’S State Materials and Tests Engineer. This manual sets out test frequency of acceptance samples and tests, sampling point, sample size, sampling and test methods and appropriate report forms for materials to be incorporated into construction projects. This Manual also contains Bureau of Materials and Tests (ALDOT) procedures referenced in the Manual and/or specifications and BMT worksheets and test report forms. (Said manual is available on ALDOT’S website)

 5. All Technical Advisories and Memorandums issued, prior to or after execution of this AGREEMENT, by ALDOT’S State Materials and Tests Engineer. The advisories convey certain practices and procedures of ALDOT relating to sampling and testing of materials used in construction projects. A copy of each advisory issued on or subsequent to execution of this AGREEMENT shall be furnished to the CONSULTANT in a timely manner by ALDOT’S Region Materials and Tests Engineer. (Said manual is available on ALDOT’S website).

 6. A tabulation of required ALDOT’S technician certifications relating to construction engineering and inspection.

7. ALDOT’S manual of Materials, Sources and Devices with Special Acceptance Requirements as issued by the State Materials and Tests Engineer. (Said manual is available on ALDOT’S website)

8. One copy of the Radiological Safety Manual for use of Nuclear Moisture/Density and Asphalt Content Gauges as issued by ALDOT’S State Materials and Tests Engineer for each project on which there is a nuclear testing device.

9. Guidelines for Operations issued by ALDOT. (Said manual is available on ALDOT’S website)

10. FHWA Manual on Uniform Traffic Control Devices.

 11. The applicable Roadway and Traffic Design Standards.

 12. The applicable Alabama Regulations for Control of Radiation Chapter 420-3-26 Radiation Control as issued by the State of Alabama Health Department.

1. The AASHTO Standard Specifications for Transportation Materials and Methods of Sampling and Testing.
2. Copies of all applicable ASTM Standards.

B. When requested by the STATE, the CONSULTANT shall furnish and maintain a Project Office within project work limits, or other location approved by the Region Engineer. The site of said office, size of office and accommodations shall have prior written approval by the Region Engineer. The office shall meet all local, state and federal building codes and requirements and shall contain the following:

1. A minimum of 600 square feet heated and cooled office space.
2. Floor space shall be divided into two restrooms, one central office, and three private offices. One of the private offices, within same confines as the CONSULTANT, shall be suitably furnished and maintained as an office for use of the STATE, if requested. This office space shall contain no less than 180 square feet. The minimum office equipment to be provided by the CONSULTANT for the STATE office shall consist of one desk and complimentary office chair; two conference room chairs; drawing table (4' x 6' minimum size); drafting stool; filing cabinets as needed and telephone service or as approved by the Region Engineer.
3. Heating, air conditioning and lighting.
4. Water cooler service (not bottled water).
5. Hot and cold water service.
6. One (1) fire extinguisher (Minimum size 10# CO2) per 200 square feet of floor space.
7. If the office is a trailer, tie-downs capable of withstanding winds up to hurricane force. (See NOTE in 603.1(a) about tie down strap requirements).
8. Office trailer underpinning with materials approved by the Region Engineer.
9. Garbage and trash disposal service.
10. Grass and weed control at office site to a maximum of three (3) inches in height by mowing for a distance of five (5) feet outside security fencing (if provided), or within boundaries as approved by the Region Engineer.
11. The CONSULTANT shall provide janitorial service.
12. Parking spaces for a minimum of eight (8) vehicles, plus additional spaces for use by the CONSULTANT’S vehicles, graded for drainage and suitably surfaced, with an all-weather access road.
13. Restroom connections to an existing sanitary sewer, a chemical holding tank, or approved septic tank.
14. The CONSULTANT shall have available, for use in the field office, a personal computer. The personal computer shall comply with at least current minimum ALDOT desktop hardware standards and shall contain a current ALDOT remote network interface device. Additionally, the computer shall be equipped with a printer conforming to current minimum ALDOT standards with 11x17 print capabilities. The said computer shall include current ALDOT standard Microsoft Office configuration, as well as, current ALDOT production versions of Bentley software. All CADD files are required to be completely compatible with the Department’s current production versions of Bentley software. In addition, the CONSULTANT shall have available tablet computers and/or smart phone for use in the field inspections and documentation, if required. The tablet computer and/or smart phone shall comply with at least current minimum ALDOT standards and have the access to the internet via an air card or Wi-Fi connection. Ownership and possession of such computers and smart phones shall remain at all times with the CONSULTANT. The CONSULTANT shall be responsible for requesting a password to access ALDOT’S computer network.

 The CONSULTANT shall also furnish such other shelter, storage and parking space as required by the Region Engineer to effectively carry out the CONSULTANT’S responsibilities under this AGREEMENT. The CONSULTANT shall provide appropriate type of vehicles in numbers as approved by the Region/Area Engineer, to accommodate the CONSULTANT’S project personnel.

Furniture and office equipment, supplied by the CONSULTANT, shall consist of desks, chairs, drafting tables, bookcases, file cabinets, calculators, facsimile machine, photo-copier, typewriters, telephones and other items determined by the Region/Area Engineer to be necessary in order to fulfill work under this AGREEMENT. The CONSULTANT shall provide all survey equipment, photographic equipment, tapes, rulers, field books and any other items necessary for satisfactory performance of work. Quantity and quality of the items require the Region Engineer’s approval. Equipment shall be either U.S. Customary or metric as directed by the Region Engineer.

Routine items for operation of the office, such as stamps, postal costs, custodial fees, utility service, etc., shall be supplied by the CONSULTANT.

6.0 LIAISON:

The CONSULTANT shall be fully responsible for fulfilling all functions assigned to it by this AGREEMENT. The CONSULTANT’S activities and decisions relating to project(s) shall be subject to review by the Region Engineer. The CONSULTANT shall provide coordination of all activities, correspondence, reports, and other communications related to its responsibilities under this AGREEMENT. No personnel shall be assigned until written notification by the Region Engineer has been issued. Construction engineering and inspection forces shall be required of the CONSULTANT at all times when required by the STATE. If construction contract is suspended, the CONSULTANT’S forces shall be adjusted at the direction of the Region Engineer to correspond with type of suspension, either complete suspension or partial suspension.

7.0 COOPERATION AND PERFORMANCE OF THE CONSULTANT:

During the period of this AGREEMENT, the STATE shall conduct reviews of various phases of the CONSULTANT’S operations, such as construction inspection, materials sampling and testing and administrative activities. Reviews shall be conducted to determine compliance with this AGREEMENT and sufficiency with which procedures are being effectively applied. These reviews are to assure that construction work and administrative activities are performed in reasonable conformity with the STATE policies, plans, specifications and contract provisions. The STATE shall have complete access, at all times, to project site, project office, all project records and any other CONSULTANT items associated with said project or this AGREEMENT. The CONSULTANT shall cooperate and assist the STATE representatives in conducting said reviews. When deficiencies are indicated in a review, immediate remedial action shall be implemented by the CONSULTANT in conformance with the STATE’S recommendations. The STATE’S remedial recommendations and the CONSULTANT’S actions are to be properly documented by the Region Engineer. The CONSULTANT shall be responsible for accuracy of its work and shall promptly implement policies and procedures reasonably necessary to prevent errors, omissions, or noncompliance with said contract terms. If the CONSULTANT’S services hereunder contain errors, omissions, or are not compliant with terms of said contract, the CONSULTANT, upon receipt of written notice of such defects from the STATE, shall correct such errors, omissions or noncompliance at its own expense. However, when the CONSULTANT is responsible for managing a project and where CONSULTANT errors, omissions or contractual lapses caused increased costs, delays, or other damages to the STATE, the Region Engineer shall prepare a written evaluation of the costs, delays or damages and circumstances that caused the increased costs, delays or damages. A copy shall be sent to the CONSULTANT. Said costs shall be deducted from the monthly payment or retainage due to the CONSULTANT. Remedial action shall be required commensurate with the degree and nature of deficiencies cited. Additional compensation to the CONSULTANT shall not be allowed for remedial action taken to correct deficiencies by the CONSULTANT. Federal Aid projects are subject to review by representatives of FHWA. Additional State personnel may make special reviews. The CONSULTANT shall fully cooperate with and assist in making such reviews.

8.0 REQUIREMENTS:

A. General:

It shall be the responsibility of the CONSULTANT to provide services as necessary for contract administration to produce construction in reasonable conformity with plans, specifications and contract provisions. The CONSULTANT shall advise the Region Engineer and shall document any omissions, substitutions, defects, and deficiencies noted in the work of the Contractor and the corrective action taken.

B. Survey Control:

The CONSULTANT may be requested to reestablish project survey controls. The CONSULTANT may be requested to provide project surveying to fulfill project requirements.

 C. Project Inspection: The CONSULTANT shall provide services to monitor and document the Contractor's construction operations. The CONSULTANT shall test, inspect and document all construction material as required to assure quality of workmanship and materials are in reasonable conformity with plans, specifications and other contract provisions. The CONSULTANT may be responsible for monitoring and approving asphalt production. The STATE shall monitor all other off-site activities and fabrication (including pre-stress production). The CONSULTANT shall keep detailed, accurate records of the Contractor's daily operations and significant events that may affect the work. The standard procedures and practices of the STATE for inspections of construction projects are set out in the STATE’S Construction Manual. The CONSULTANT shall have appropriate certifications for inspection of work being performed. The CONSULTANT shall in general, perform inspection services in accordance with these standard procedures and practices and other accepted practices as may be appropriate.

1. Testing:

 The CONSULTANT shall perform sampling and testing of component materials and completed work items to the extent that will assure materials and workmanship incorporated in each project is in reasonable conformity with plans, specifications and contract provisions. The CONSULTANT shall meet minimum sampling frequencies set out in the STATE’S Testing Manual. The STATE reserves the right to require additional sampling and testing. The CONSULTANT shall be specifically responsible for securing job control samples and utilizing test results to determine acceptability of all materials and completed work items. The CONSULTANT shall be responsible for verification of a certified test report as determined by the Bureau of Materials and Tests, DOT label, DOT stamp, etc., as appropriate. The CONSULTANT shall be responsible for progress record sampling of reinforcing steel. The STATE shall monitor the effectiveness of the CONSULTANT’S testing procedures through surveillance and obtaining testing progress record samples and final record samples. Progress record sampling and testing is necessary to verify job control sampling frequencies and test procedures are adequate. The CONSULTANT shall inform the STATE of schedules for sampling and testing as work progresses on each construction contract so sampling can be accomplished by the STATE at the proper time. Sampling and testing shall be as required by the aforementioned ALDOT Testing Manual or as modified by contract provisions. The CONSULTANT shall be responsible for transporting samples to be tested to the appropriate State laboratory. Any testing performed at a laboratory other than the State laboratory shall be handled in a separate AGREEMENT. The CONSULTANT shall perform all required and necessary surveillance, inspection and documentation of project hot-mix asphalt operations.

E. Management Engineering Services:

The CONSULTANT shall perform all management engineering services necessary to: assure proper coordination of activities of all parties involved in accomplishing completion of projects; maintain complete, accurate records of all activities and events relating to projects; properly document all significant changes to projects; provide interpretations of plans, specifications and contract provisions; make recommendations to the STATE to resolve disputes that may arise in relation to construction contracts; and to maintain an adequate level of surveillance of the Contractor's activities. The CONSULTANT shall perform any other management engineering services normally assigned to a project that are required to fulfill the CONSULTANT’S responsibilities under this AGREEMENT. All recordation and documentation shall be in accordance with standard ALDOT procedures, formats and content. CONSULTANT services include, but are not limited to the following:

 1. Attending and participating in a pre-construction conference for each project. Record significant information revealed and decisions made at conference and if requested by the STATE, distribute copies of said minutes to appropriate parties. The CONSULTANT may be required to conduct the pre-construction conference.

 2. Complete and maintain a full and accurate daily record of all activities and events relating to project. Record all work completed by the Contractor, including quantities of pay items in conformity with the Construction Manual, Construction Information Memorandums, and CAMMS Policies and Procedures. The CONSULTANT shall immediately report to the Region Engineer changes in pay items, project time or cost as soon as they become known to the CONSULTANT.

 3. Complete and maintain Project Diaries and Inspector's Daily Reports as requested by the STATE. **Said diaries and reports shall be kept up-to-date on a daily basis**.

 4. Maintain a project log of all materials entering into work with proper indication of basis of acceptance for each shipment of material.

 5. Maintain project records of all sampling and testing accomplished. Analyze such records to ascertain acceptability of materials and completed work items. The field reports shall be recorded in project records within three days. The CONSULTANT shall verify, certify and document work items requiring performance periods (curing period, operational period, etc.).

 6. Prepare and submit monthly to the Region Engineer a comprehensive tabulation of the quantity of each pay item satisfactorily completed that includes appropriate test reports and/or materials certifications or materials stored to date. Quantities shall be based on daily records and calculations. Calculations shall be properly recorded. The tabulations shall be used for preparation of the Monthly Progress Estimate.

 7. Provide interpretations of plans, specifications and contract provisions. The CONSULTANT shall consult with the Region Engineer when an interpretation involves complex issues or may have an impact on cost or quality of performing said work.

 8. Field problems are difficulties encountered during construction through circumstance, which may or may not be under the control of the Contractor, requiring a degree of engineering evaluation and decision. Field problems might involve situations such as: out of place piling, out of tolerance work, out of specification materials, structural defects, accidental damage, underground obstructions, etc. These problems may have a significant impact upon the execution, progress, cost or quality of said project. Therefore, it is of paramount importance that problems be resolved expeditiously. The CONSULTANT shall ensure solutions are pursued and implemented as expeditiously as possible. Where a difficulty, problem, or defect of any nature is encountered during construction, the CONSULTANT shall assemble all relevant information to include any proposals from the Contractor. The CONSULTANT shall document and evaluate the same in a concise and orderly manner, by reviewing all information and circumstances. The CONSULTANT shall make recommendations to the Region Engineer for the most expeditious course of action to minimize delays and costs while achieving a structurally acceptable result.

The Engineer of Record (Design Engineer) or State Construction Engineer, depending on the nature of proposal is responsible for structural engineering analysis of the Contractor's proposals, determining acceptability of proposals and meeting the requirements of said design. However, the CONSULTANT shall be responsible for ensuring that the Region Engineer is provided with all relevant information and, in addition, shall appraise and make recommendations to the Region Engineer of all project(s) related circumstances that may have an influence upon the solution.

In particular, the CONSULTANT shall first utilize his own personnel and resources in order to assess the problem and its likely impacts on said project(s). By utilizing CONSULTANT personnel and resources, the CONSULTANT shall assess both technical and contractual implications upon said project(s) of any proposals presented by the Contractor. The CONSULTANT shall consider all likely impacts upon project(s) as regards to costs, delays, potential claims, contract administration, management, any justifiable financial adjustments (increases or decreases, including penalties) to be applied to Construction Contract, and feasibility of the Contractor successfully and expeditiously fulfilling his technical proposals. The CONSULTANT shall make these assessments in order to formulate his recommendations. The CONSULTANT shall then forward the said assessments and recommendations to the Region/Area Engineer, together with any proposals from the Contractor. The CONSULTANT shall be a liaison and cooperate with the STATE in resolution of any problems. Upon resolution and approval of technical solution, the CONSULTANT shall ensure all approved remedial measures are completed in a technically competent and satisfactory manner. The CONSULTANT shall be responsible for any contract administration and management normally associated with implementing remedial measures. In situations where the CONSULTANT does not have direct responsibility for engineering inspection of the item that caused said problem, but where that item is now under his area of control, (example: defective precast components or fabricated steelwork made at a facility under engineering inspection of a different party and later delivered to site), the CONSULTANT shall formulate his assessment and recommendations and cooperate in resolving the problem.

In all situations, the CONSULTANT shall ensure all proposals, reviews, assessments, studies, recommendations and decisions are executed expeditiously in order to minimize any delays and costs.

 9. The CONSULTANT shall analyze changes to plans, specifications or contract provisions and extra work that appear to be necessary to fulfill the intent of said contract. The CONSULTANT shall provide recommended changes to the Region Engineer for approval. Approval of the Region Engineer must be obtained prior to initiating any change or extra work.

 10. When a modification to the original contract for a project is required, due to a necessary change in character of work, the CONSULTANT, in conjunction with the Area Construction or Local Transportation Engineer, shall negotiate prices with the Contractor and prepare and submit a recommendation to the Region Engineer for approval. The Region Engineer shall prepare the required SUPPLEMENTAL AGREEMENT and obtain all required approvals.

 11. In the case where the Contractor gives notice, either written or verbal, that certain work to be performed is beyond the scope of construction contract and intends to claim additional compensation, the CONSULTANT shall maintain accurate documentation in accordance with Section 110 of the Standard Specification, of the costs involved in such work.

 12. In the case where the Contractor for a project submits a claim for additional compensation, the CONSULTANT shall analyze submittal in conjunction with the Region Construction Engineer. The CONSULTANT may be required to provide recommendation on validity and reasonableness of the requested additional compensation and/or contract time extension. The CONSULTANT shall maintain complete and accurate documentation of work involved in claims.

 13. In the case where the Contractor for a project submits a request for an extension of allowable contract time, the CONSULTANT shall the analyze request and prepare a recommendation to the Region Engineer covering accuracy of statements and actual effect of delaying factors on completion of controlling work items. The CONSULTANT shall make recommendations weekly, or at other times as necessary, to the Region Engineer on all delays. This recommendation is needed to justify a time extension.

 14. The CONSULTANT shall prepare and submit to the Region Engineer a final estimate with documentation and one (1) set of record as-built plans for each contract. All changes made to plans, which involve the CONSULTANT, shall be signed and sealed by the CONSULTANT and the Region Engineer. This task must be completed within a timely manner or in accordance with current ALDOT Standard Specifications from the earliest project acceptance date.

 15. At request of the STATE, the CONSULTANT shall assist appropriate STATE offices in preparing for hearings or litigation that may occur during the term of this AGREEMENT in connection with a project covered by this AGREEMENT.

 16. The CONSULTANT shall monitor and document the Contractor's compliance with contract provisions in regard to payment of predetermined wage rates in accordance with State procedures. This includes sub-contractor compliance.

 17. The CONSULTANT shall review and document the Contractor's compliance with contract requirements concerning Equal Employment Opportunity and Affirmative Action; assist the STATE’S Equal Employment Opportunity Specialist as requested; and, review and document D.B.E. (Disadvantaged Business Enterprises) activities to insure compliance of contract goals.

 18. The CONSULTANT shall review and document each construction project to the extent necessary to determine whether construction activities violate requirements of any permits. The Project Manager shall notify the Contractor, in writing, of any violations or potential violations and require his immediate resolution of said problem. Violations shall be reported to the Region Engineer immediately.

 19. Shop drawing/sample submittal and approvals shall be logged by the STATE. Tracking shall include maintaining a log book of the status of each submittal as it progresses through review and approval. The CONSULTANT shall actively encourage all reviewers to accomplish reviews promptly.

 20. The CONSULTANT shall assist the Contractor and utility companies in resolving conflicts so that any conflicting utilities are timely removed, adjusted or protected to minimize delays to construction operations. Documentation shall be maintained in accordance with the STATE’S procedures.

 21. The Project Manager and the CONSULTANT for each particular project shall conduct meetings as required with respective Contractor, sub-contractor and/or utility companies to review plans, schedules, problems or other areas of concern. The results of these meetings shall be recorded in project diary.

 22. The CONSULTANT may be required to conduct and document field reviews of maintenance of traffic operations after normal working hours, weekends and holidays.

 23. The CONSULTANT may be required to respond to inquiries from various persons, i.e., public, media, property owners, local agencies, State agencies, Federal agencies, etc., and inform the Region Engineer of these inquiries.

 24. The CONSULTANT may be required to provide field construction activities in areas of design engineering, vertical and horizontal control, typical sections, cross-sections for monthly estimates and other engineering required to complete construction project.

9.0 PERSONNEL:

A. General Requirements:

The CONSULTANT shall provide a sufficient number of qualified personnel as directed by the STATE to effectively carry out its responsibilities under this AGREEMENT.

1. Personnel Qualifications:

The CONSULTANT shall utilize only competent personnel who are qualified by experience and education. The CONSULTANT shall submit, in writing, to the Region/Area Engineer the name of all personnel to be considered for assignment to said construction projects, together with a detailed resume of each person’s qualifications and copies of current certifications with respect to salary, education and experience. The CONSULTANT’S personnel approval request shall be submitted at least two weeks prior to and approved by the Region Engineer prior to the date an individual is to report to work. Listed below are minimum qualifications and job descriptions for the CONSULTANT’S personnel that may be working on various projects under this AGREEMENT.

PROJECT MANAGER:

Minimum Qualifications:

* Ten years of experience in construction inspection, surveying or highway materials testing and inspection or a Bachelor of Science degree in Civil Engineering or Registered Professional Engineer with experience in construction inspection, surveying or highway materials testing and inspection. One or more of the following certifications may be required as approved by the Region Engineer.
* Certified Asphalt Technician Level I – Field Tester
* Certified Level II – Quality Management Technician
* Certified Asphalt Roadway Technician
* Work Zone Safety Certification
* Certified Concrete Technician (ACI and ALDOT certification)
* Radiological Safety Course Certification
* Qualified Credentialed Inspector (QCI)

 Job Description:

This is administrative and technical work in Civil Engineering. The employees in said class shall act as the first contact between contractor and the STATE. The Project Manager shall be responsible for supervision of all employees assigned to the said project. The Project Manager shall ensure that a project is built in accordance with project plans and specifications under which contract was awarded. The Project Manager shall report directly to the District Manager’s or the Region Engineer’s designated representative.

 SENIOR INSPECTOR:

 Minimum Qualifications:

* Eight years of experience in construction inspection, surveying or highway materials testing and inspection or a Bachelor of Science degree in Civil Engineering or Registered Professional Engineer with two years of experience in construction inspection, surveying or highway materials testing and inspection. One or more of the following certifications as necessary and approved by the Region Engineer. Inspectors who are to perform a specific task shall be certified in said field.
* Certified Asphalt Technician Level I – Field Tester
* Certified Level II – Quality Management Technician
* Certified Concrete Technician (ACI and ALDOT Certification)
* Certified Asphalt Roadway Technician
* Work Zone Safety Certification
* Radiological Safety Course Certification
* Qualified Credentialed Inspector (QCI)

Job Description:

This is skilled sub-professional engineering work in the field or office. Employees in said class shall act as the Assistant Project Manager and be responsible for reviewing and directing inspection duties of all project inspectors. The Senior Inspector shall be capable of surveying and drafting, as they apply to documenting and inspection, of a construction project. The Senior Inspector shall report directly to Project Manager.

 LEVEL II INSPECTOR:

 Minimum Qualifications:

* Five years of experience in construction inspection, surveying or highway materials testing and inspection or a Bachelor of Science degree in Civil Engineering with one year of experience in construction inspection, surveying or materials testing and inspection. One or more of the following certifications as necessary and approved by the Region Engineer. Inspectors who are to perform a specific task shall be certified in said field.
* Certified Asphalt Technician Level I – Field Tester
* Certified Concrete Technician (ACI and ALDOT Certification)
* Certified Asphalt Roadway Technician
* Work Zone Safety Certification
* Radiological Safety Course Certification
* Qualified Credentialed Inspector (QCI)

Job Description:

This is skilled sub-professional engineering work in the field or office. Employees in said class shall follow standard procedures in documenting construction projects and inspecting job activities to verify they are in compliance with project plans and specifications. The inspector shall be responsible for completing a daily report documenting labor and equipment used by contractor to include a description of work performed and any pertinent conversations with contractor. The inspector will assist with office work such as plotting cross-sections and computing earthwork quantities. The inspector shall report directly to Senior Inspector and/or Project Manager.

LEVEL I INSPECTOR:

 Minimum Qualifications:

* Some experience in construction inspection, surveying or highway materials testing and inspection is preferred. One or more of the following certifications as necessary and approved by the Region Engineer. Inspectors who are to perform a specific task shall be certified in that particular field.
* Certified Asphalt Technician Level I – Field Tester
* Certified Concrete Technician (ACI and ALDOT Certification)
* Certified Asphalt Roadway Technician
* Work Zone Safety Certification
* Radiological Safety Course Certification

 Job Description:

This is sub-professional engineering work in the field or office. Employees in said class shall follow standard procedures in documenting construction projects and inspecting job activities to verify they are in compliance with project plans and specifications. The inspector shall be responsible for completing a daily report documenting labor and equipment used by contractor to include a description of work performed and any pertinent conversations with contractor. The inspector shall assist with office work such as plotting cross-sections and computing earthwork quantities. The inspector shall report directly to Senior Inspector and/or Project Manager.

 ADMINISTRATIVE ASSISTANT

 Minimum Qualifications:

* A high school diploma or a GED certificate.

Job Description:

Employees in this class may perform a variety of clerical duties. These duties may include data entry, filing documents, sorting mail, typing documents, taking dictation, proofreading documents, making copies, greeting and directing the public, taking telephone messages, posting records, or making simple calculations.

PROFESSIONAL CIVIL ENGINEER

Minimum Qualifications:

* Must possess a Professional Engineer’s License as issued by the Alabama State Board of Licensure for Professional Engineers and Land Surveyors and must have at least one year of professional civil engineering experience.
* Qualified Credentialed Inspector (QCI)

Job Description:

This is advanced professional work in the field of civil engineering. Employees in said class perform a variety of complex engineering duties associated with planning, geodetic surveys, location, design, construction or maintenance of roads, bridges, buildings, or other civil engineering projects.

 TARGET PERSON

 Minimum Qualifications:

* Six months experience in surveying.

Job Description:

This is sub-professional work in the field or office. Employees in said class follow standard procedures in carrying out field or office assignments related to surveying for construction projects. Limited instrument use for construction and right-of-way stakeout, obtaining quantity cross-sections, spot checking location and elevation of different construction activities such as form work, setting of girders, pipe grades and blue top elevations as well as cutting line constitute the main activities.

 INSTRUMENT PERSON

 Minimum Qualifications:

* Two years experience in surveying.

Job Description:

This is skilled sub-professional surveying work in the field or office. Employees in said class follow standard procedures in carrying out field or office assignments related to surveying for construction projects. Employees in said class may be in charge of checking of contractor’s work, obtaining quantity cross-sections, and staking right-of-way. Said employee must be able to operate several types of surveying equipment. The ability to read/comprehend contract plans, take and reduce field notes and complete daily reports is essential. The position shall report directly to Field Supervisor or Project Manager.

 FIELD SUPERVISOR

 Minimum Qualifications:

* Four years experience in surveying with at least one year of experience as a construction survey party chief.

Job Description:

This is supervisory and technical surveying work in the field or office. Employees in said class are in charge of making daily work assignments, interpreting and reading construction plans, and directing surveying activities involved with checking contractor’s work, obtaining quantity cross-sections, and staking right-of-way. Work is performed with considerable independence, but is reviewed for conformance with established policies, procedures, and applicable State laws. The ability to calculate horizontal and vertical positions as well as quantities for payment, communicate in writing and orally, and instruct personnel in the use of equipment is essential. Said position shall report directly to Project Manager or Professional Land Surveyor

PROFESSIONAL LAND SURVEYOR

Minimum Qualifications:

* Must possess a Professional Land Surveyor’s License as issued by the Alabama State Board of Licensure for Professional Engineers and Land Surveyors and have at least one year of experience as a Professional Land Surveyor.

Job Description:

This is supervisory professional surveying work in the field or office as required by Alabama State Law. Employees in said class shall insure compliance to standards of practice for surveying in the State of Alabama and conformance with established policies and procedures for surveys which involve the staking of right-of-way.

 C. STAFFING:

The STATE shall determine number and type of personnel needed to adequately staff and carry out responsibilities of said scope of service. The qualifications of each person proposed for assignment must be reviewed and approved in writing by the Region Engineer. An individual previously approved whose performance is later determined by the STATE to be unsatisfactory shall be immediately removed and replaced by the CONSULTANT within one week after notification. The CONSULTANT shall maintain an appropriate staff, as approved by the Region Engineer, after completion of construction to complete the final estimate. Qualified personnel, thoroughly familiar with all aspects of construction and final measurements of various pay items, shall be available to resolve disputed final pay quantities until appropriate contract is finalized.

As the Contractor's operations on a contract diminish, the CONSULTANT shall reduce number of personnel assigned to said project as appropriate. Any adjustment of the CONSULTANT forces as directed by the Region Engineer shall be accomplished within one week after notification. The CONSULTANT shall, at all times, provide project personnel to ensure proper staffing is maintained. Personnel on a specific project shall be rotated to keep overtime to a minimum. The Project Manager shall be responsible to schedule the CONSULTANT employee work hours to avoid overtime. This shall include varying employee work hours, or the use of shift work, or rescheduling employee normal work hours in advance of expected overtime. The method of schedule modification shall be approved by the Region Engineer. If overtime is not held to a minimum, then SECTION 1, 7.0 (Cooperation and Performance of the CONSULTANT) of this AGREEMENT shall be enforced to replace personnel. If construction contract is suspended, the CONSULTANT’S forces shall be adjusted at the direction of the Region Engineer to correspond with type of suspension. In the event of a construction contract suspension which requires the removal of CONSULTANT forces from project, the CONSULTANT shall be allowed up to a maximum of five (5) days to demobilize, relocate or terminate such forces.

Should the STATE determine a need for additional classifications not set forth in this AGREEMENT, the classifications and hourly pay ranges shall be established based on mutual AGREEMENT with the CONSULTANT.

D. CERTIFICATION - Licensing for Equipment and Personnel:

The CONSULTANT shall be responsible for obtaining proper certification and licenses for equipment and personnel used on any project. Licensing of nuclear testing devices shall be obtained through the appropriate agencies. Only technicians approved by the STATE shall be authorized to operate nuclear testing devices. The CONSULTANT shall be responsible for monitoring activity (i.e. film badges/radiation levels) of their technicians who operate nuclear testing devices. Other certifications for technicians such as concrete, Asphalt Roadway, Asphalt Plant, American Traffic Safety Services Association (ATSSA) Worksite Supervisors and others if applicable shall be required. Construction Inspectors work qualifications shall be as shown in SECTION 1, Paragraph 9.0 B of this AGREEMENT.

10.0 SUBCONSULTANT SERVICES:

Upon written approval of the STATE and prior to performance of work, the CONSULTANT may subcontract for engineering surveys, materials testing, or specialized professional services. The Region Engineer shall verify qualifications of personnel used by sub-consultant.

11.0 OTHER SERVICES:

The CONSULTANT shall, upon written authorization by the Region Engineer, perform any additional services not otherwise identified in this AGREEMENT as may be required by the STATE in connection with said Project(s).

12.0 CLAIMS REVIEW:

 In the event the Contractor for said project submits a claim for additional compensation and/or time after the CONSULTANT shall, by written request from the STATE, analyze the claim, prepare recommendation to the Region Engineer covering validity and reasonableness of charges and/or assist in negotiations leading to the settlement of said claim. Compensation for these services shall be mutually agreed between the STATE and the CONSULTANT prior to performance of said Services.

1. The CONSULTANT shall, upon written request by Region Engineer, assist appropriate STATE Offices in preparing for arbitration hearings or litigation that occur after the CONSULTANT’S contract time in connection with the project covered by this AGREEMENT.

 The CONSULTANT shall, upon written request by Region Engineer, provide qualified

Engineers and/or Engineering Technicians to serve as engineering witnesses, provide exhibits, and otherwise assist the STATE in any litigation or hearings in connection with said construction contract(s).

**ARTICLE II - TIME OF BEGINNING AND COMPLETION**

1. The CONSULTANT services for each on-call construction assignment shall begin after the CONSULTANT receives approved Purchase of Consultant Services for Construction Engineering and Inspection order (Form CPO – CE&I) from Region Engineer. The CPO shall constitute Notice to Proceed from the STATE. The maximum amount payable to the CONSULTANT for services on each on-call construction assignment shall not exceed the amount stated on said CPO. The length of services as herein established for each construction contract is based on the CONSULTANT beginning work when notified and continuing work until acceptance by the STATE of described services.
2. This AGREEMENT shall be effective upon the date of approval by the Legislative Contract Review Oversight Committee, and signature of the Governor of Alabama, for a term of two years. Any requests for work by the STATE, made prior to the end of the two-year term shall be covered by this AGREEMENT.

# ARTICLE III – PAYMENT

## SECTION 1

 Overhead shall be limited to the actual audited overhead rates. Salary increases shall be limited to a maximum of five (5) percent per year. Profit will be maintained at ten (10) percent of these costs. When the STATE requires the CONSULTANT to stay overnight at a project, the CONSULTANT will be reimbursed for actual expenses up to the maximum allowable by State Law. Employees whose vehicles are used for work-related mileage (excluding mileage for commuting) will be compensated at the prevailing Federal mileage rate as approved by the General Services Administration. Out-of-pocket expenses, not to exceed $100.00, will be paid as direct cost plus ten (10) percent. Purchases over $100.00 will require written authorization from the STATE.

For performance by the CONSULTANT of the services provided for in this AGREEMENT, and as full and complete compensation therefore, including all approved expenditures and expenses incurred by the CONSULTANT in connection with this AGREEMENT, and subject to conformity with all provisions of this AGREEMENT, the STATE will pay the CONSULTANT as follows:

1. The total compensation to the CONSULTANT for work provided for when performed under this AGREEMENT will be as follows:
2. Direct salary and wages – Actual salary and wages paid personnel while actually engaged in performance of work, all as determined by Finance Director of the Alabama Department of Transportation. Listed below are labor rate ranges for the CONSULTANT’S personnel that may be working on various projects under this AGREEMENT.

 CLASSIFICATION HOURLY PAY RANGES

 Professional Civil Engineer $30.00 to $45.00

 Project Manager $21.00 to $37.00

 Senior Inspector $17.00 to $29.00

 Level II Inspector $13.00 to $24.00

 Level I Inspector $12.00 to $19.00

 Professional Land Surveyor $26.00 to $40.00

 Field Supervisor $20.00 to $36.00

 Instrument Person $13.00 to $24.00

 Target Person $12.00 to $19.00

 Administrative Assistant $11.00 to $19.00

1. All other related direct actual costs paid by the CONSULTANT, applicable to this AGREEMENT, such as printing and reproduction, and subsistence of personnel engaged on project at rates payable under state law, and for those supplies, communication equipment, etc. not included in the overhead rate. Vehicles reimbursed for work-related mileage (excluding mileage for commuting) at the prevailing Federal mileage rate as approved by the General Services Administration, see Attachment #1 for ALDOT Consultant Field Office Procedures, which Attachment #1 is made a part hereof.
2. For work performed out of the CONSULTANT’S home or branch office, the CONSULTANT’S home office overhead and labor additive rate of 000.000 percent (for Fiscal Year Ending\_\_\_\_\_\_) shall be applied to direct salary and wages. Home office Facilities Capital Cost of Money (FCCM) rate is 0.00 percent (for Fiscal Year Ending 9-28-2018) of the direct labor and no profit shall be allowed on the said item. Any sub-consultant’s overhead and labor additive rate shall not exceed prime consultant’s rate. This rate shall be fixed for the life of the AGREEMENT unless revised by SUPPLEMENTAL AGREEMENT.
3. For work performed out of STATE provided facility, the CONSULTANT’S field office and labor additive rate of 000.00 percent (for Fiscal Year Ending\_\_\_\_\_\_) shall be applied to the direct salary and wages. Field office Facilities Capital Cost of Money (FCCM) rate is 0.00 percent (for Fiscal Year Ending 9-28-2018) of the direct labor and no profit shall be allowed on the said item. Any sub-consultant’s overhead and labor additive rate shall not exceed prime consultant’s rate. This rate shall be fixed for the life of the AGREEMENT unless revised by SUPPLEMENTAL AGREEMENT. (*NOTE: For CONSULTANTS that have not provided an audited field office overhead rate, the billable field office rate shall be 105.00 percent until such time as one is provided to the STATE’S Bureau of Finance and Audits, External Audit Section.)*
4. For work performed out of STATE provided facility, the CONSULTANT’S geotechnical office and labor additive rate of 106.96 percent (for Fiscal Year Ending 9-28-2018) shall be applied to the direct salary and wages. Geotechnical office Facilities Capital Cost of Money (FCCM) rate is 0.00 percent (for Fiscal Year Ending 9-28-2018) of the direct labor and no profit shall be allowed on the said item. Any sub-consultant’s overhead and labor additive rate shall not exceed prime consultant’s rate. This rate shall be fixed for the life of the AGREEMENT unless revised by SUPPLEMENTAL AGREEMENT. *(NOTE: For CONSULTANTS that have not provided an audited geotechnical office overhead rate, the billable geotechnical office rate shall be 125.00 percent until such time as one is provided to the STATE’S Bureau of Finance and Audits, External Audit Section.)*
5. Profit at the rate of ten (10) percent applied to direct salary, overhead, and approved expenses, except for the cost of sub-consultants, which is limited to a five (5) percent administrative fee.
6. The STATE’S Bureau of Finance and Audits, External Audit Section shall be furnished a Statement of Direct Labor, Fringe Benefits and General Overhead that is in compliance with Generally Accepted Accounting Principles and an audited Statement of Indirect Cost developed in compliance with the Contract Cost Principles and Procedures stated in Volume 1, Federal Acquisition Regulations, Part 31, and the audit standards contained in the Government Auditing Standards issued by the Comptroller General of the United States by the end of the fifth month after the closing of the CONSULTANT’S fiscal year.
7. Any paid overtime shall require prior authorization from the Region Engineer. Billable overtime is all time worked over Forty Hours each week or holidays observed by the CONSULTANT.

For firms that include the premium portion of direct labor overtime in the Direct Labor Base of the Indirect Cost Rate Calculation:

1. The hourly overtime rate will be 1.5 times the billable rate.
2. Hours worked on holidays observed in the Region on the work that is being performed by the CONSULTANT will be billable at an hourly rate of 2 times the regular billing rate.

For firms that do not include the premium portion of direct labor overtime in the Direct Labor Base of the Indirect Cost Rate Calculation:

1. The hourly rate will be one 1 times the billable rate.
2. The premium portion of overtime will be billed in accordance with the CONSULTANT’S Indirect Cost Rate Calculation.

9. The maximum amount payable, to the CONSULTANT for work provided for under this AGREEMENT, shall not exceed Zero Hundred Thousand and no/100 Dollars ($000,000.00).

### SECTION 2

1. Certified copies of daily payrolls for personnel actively engaged on work included in this specific Rate of Pay AGREEMENT shall be furnished monthly.
2. Payments to the CONSULTANT shall be made not more often than monthly. Payment shall be subject to submission by the CONSULTANT of such vouchers or invoices, daily progress reports and such evidence of performance the STATE may deem necessary. The original invoice and (3) three copies shall be submitted by the CONSULTANT to the Region/Area Office for review, approval and forwarding to the STATE’S Bureau of Finance and Audits, External Audit Section located in Montgomery, Alabama, for payment.
3. The CONSULTANT shall correlate and coordinate accounting of CONSULTANT to comply with current audit system of the STATE and applicable Federal Acquisition Regulations. Since this is a cost reimbursable type of AGREEMENT, all direct job costs, and labor costs charged to the said project shall be the actual rate of pay at the time work is performed and shall be subjected to audit by the STATE.

## SECTION 3

 The acceptance by the CONSULTANT of the final payment shall constitute and operate as a release to the STATE of all claims and of any and all liability of the STATE to the CONSULTANT, its representatives and/or assigns for all things done, furnished or relating to services rendered by the CONSULTANT under, or in connection with this AGREEMENT, or any part thereof, provided that no unpaid invoices exist because of extra work required at the request of the STATE.

## SECTION 4

 During the period of this AGREEMENT, the CONSULTANT shall not be employed, and CONSULTANT’S employees shall not be employed, by construction contractors performing work on state or federal-aid projects on which the CONSULTANT is assigned without approval in writing by the STATE.

## SECTION 5

 The work to be performed under this AGREEMENT shall not include any work payable to the CONSULTANT under any other AGREEMENT(S) with the STATE in effect at the time work is performed.

# ARTICLE IV – MISCELLANEOUS PROVISIONS

 Exhibits A, B, C, D, E, F, G, H, I, K, L, M, N, O, P, Q, R and S attached hereto, are made a part of this AGREEMENT and the terms and provisions of such exhibits are binding on the parties respectively as fully and completely as they would bind the parties if such terms and provisions were set forth in writing in the AGREEMENT.

By signing this contract, the contracting parties affirm, for the duration of the agreement, that they will not violate federal immigration law or knowingly employ, hire for employment, or continue to employ an unauthorized alien within the State of Alabama. Furthermore, a contracting party found to be in violation of this provision shall be deemed in breach of the agreement and shall be responsible for all damages resulting there from.

In the event of any dispute between the parties, senior officials of both parties shall meet and engage in a good faith attempt to resolve the dispute. Should that effort fail and the dispute involves the payment of money, a party’s sole remedy is the filing of a claim with the Board of Adjustment of the State of Alabama.

For any and all other disputes arising under the terms of this contract which are not resolved by negotiation, the parties agree to utilize appropriate forms of non-binding alternative dispute resolution including, but not limited to, mediation. Such dispute resolution shall occur in Montgomery, Alabama utilizing where appropriate, mediators selected from the roster of mediators maintained by the Center For Dispute Resolution of the Alabama State Bar.

In WITNESS WHEREOF, the Parties hereto have caused this AGREEMENT to be executed by those officers, officials and persons thereunto duly authorized, and the AGREEMENT is deemed to be effective on the date of approval by the Legislative Contract Review Oversight Committee and the approval of the Governor of Alabama.

**ATTEST:**  **(CONSULTANT)**

By:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(Affix Corporate Seal)

**THIS AGREEMENT HAS BEEN LEGALLY REVIEWED**

**AND APPROVED AS TO FORM AND CONTENT.**

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

William F. Patty

Chief Counsel

Department of Transportation

**RECOMMENDED FOR APPROVAL:**

 STATE OF ALABAMA

 acting by and through its

 DEPARTMENT OF

 TRANSPORTATION

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Clay P. McBrien, P.E.

State Office Engineer \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

 John R. Cooper

 Transportation Director

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

George H. Conner, P.E.

Deputy Director, Operations

 The within and foregoing instrument is hereby approved on this \_\_\_\_\_\_\_\_\_\_\_\_

Day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, 20\_\_\_\_.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Kay Ivey

**GOVERNOR, STATE OF ALABAMA**

*Prepared By:*

***The Alabama Department of Transportation***

*Design Bureau-Contract Management Group*

*1409 Coliseum Boulevard*

*Montgomery, Alabama 36110*

*Office: (334)242-6842 or 6142 Fax: (334) 353-6513*

*Reference: County/Contract ID#0000, Original*